## initial gantt chart
Gantt Chart v.2 | [8 empty] | Estimate |  |  |  | Actual |  |  |  | Holidays |  |  |  | Exam Period
[11 empty] | Submitted Deliverable | [7 empty] | Unsubmitted Delivarable
# | TASKS | ASSIGNED TO | ESTIMATED START | ESTIMATED END | ACTUAL START | ACTUAL END | TASK COMPLETION % | Semester I
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | D1: Project Brief | All | 2013-10-01 | 2013-10-07 | 2013-10-01 | 2013-10-07 | 100% | bar: Semester I 1 to Semester I 2
2 | Project Management | All | 2013-10-01 | 2013-12-08 | 2013-10-07 | 2013-10-13 | 95% | bar: Semester I 1 to Semester I 2; Semester I 6; Semester I 10
2.1 | Documentation management | All |  | 2013-10-13 |  | 2013-10-13 | 100% | bar: Semester I 1 to Semester I 2
2.2 | Setup source code repository | SA |  |  |  |  | 100% | bar: Semester I 1 to Semester I 2
2.3 | Risk analysis | CJ |  |  |  |  | 100% | bar: Semester I 1 to Semester I 2
2.4 | Skills analysis | CJ |  |  |  |  | 100% | bar: Semester I 1 to Semester I 2; Semester I 13; Semester I 17
2.5 | Gantt chart | All |  | 2013-12-08 |  | 2013-10-13 | 75% | bar: Semester I 1 to Semester I 2; Semester I 6; Semester I 10; Semester I 13; Semester I 17
3 | Background | All | 2013-10-01 | 2013-10-21 | 2013-10-07 | 2013-10-21 | 100% | bar: Semester I 1 to Semester I 3; Semester I 13; Semester I 17
3.1 | Requirements gathering | All |  |  |  |  | 100% | bar: Semester I 1 to Semester I 3; Semester I 13; Semester I 17
3.2 | Accessibility and usability research | CF |  |  |  |  | 100% | bar: Semester I 1 to Semester I 3; Semester I 13; Semester I 17
3.3 | Raspberry Pi for education research | KN |  |  |  |  | 100% | bar: Semester I 1 to Semester I 3; Semester I 13
3.4 | CECIL research | SA |  |  |  |  | 100% | bar: Semester I 1 to Semester I 3; Semester I 13
3.5 | Existing systems research | CJ |  |  |  |  | 100% | bar: Semester I 1 to Semester I 3; Semester I 13
4 | Design | All | 2013-10-14 | 2013-10-20 |  |  | 68.75% | bar: Semester I 3 to Semester I 4; Semester I 13
4.1 | Requirements analysis | SA + CF |  |  | 2013-10-16 | 2013-10-17 | 100% | bar: Semester I 3 to Semester I 4
4.2 | Wireframes | All |  |  |  |  | 100% | bar: Semester I 3
4.3 | UML diagrams | All |  |  |  |  | 37.5% | bar: Semester I 3 to Semester I 4; Semester I 13
4.3.1 | Use case diagram | CF |  |  | 2013-10-19 | 2013-10-20 | 100% | bar: Semester I 3; Semester I 13
4.3.2 | Activity diagram | KN |  |  |  |  | 0% | bar: Semester I 4; Semester I 13
4.3.3 | Class diagram | CJ |  |  |  |  | 50% | bar: Semester I 4; Semester I 13
4.3.4 | Sequence diagram | SA |  |  |  |  | 0% | bar: Semester I 4; Semester I 13
5 | D2: Progess Seminar I | KN+SA+CJ | 2013-10-17 | 2013-10-23 | 2013-10-17 | 2013-10-23 | 100% | bar: Semester I 3 to Semester I 4; Semester I 13
6 | Implementation | All | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 18.13% | bar: Semester I 3 to Semester I 8; Semester I 13
6.1 | Model | SA+CF | 2013-10-14 | 2013-11-03 | 2013-10-14 |  | 42.5% | bar: Semester I 3 to Semester I 5
6.1.1 | Lexer/parser | SA |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5
6.1.2 | Compiler | SA+CF |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5
6.1.3 | Simulator | SA+CF |  |  |  |  | 10% | bar: Semester I 3 to Semester I 5
6.2 | View | KN | 2013-10-21 | 2013-11-17 |  |  | 0% | bar: Semester I 4 to Semester I 7
6.2.1 | Input editor | KN |  |  |  |  | 0% | bar: Semester I 4 to Semester I 7
6.3 | Controller | CJ | 2013-10-21 |  | 2013-10-21 |  | 30% | bar: Semester I 4 to Semester I 7
6.4 | I/O port stubs | SA | 2013-11-17 | 2013-11-24 |  |  | 0% | bar: Semester I 8
7 | Testing | All | 2013-10-14 | 2013-12-01 | 2013-10-14 |  | 3.333% | bar: Semester I 3 to Semester I 9
7.1 | User evaluation |  | 2013-11-25 | 2013-12-01 |  |  | 10% | bar: Semester I 9
7.2 | Unit testing |  | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 0% | bar: Semester I 3 to Semester I 7
7.3 | Integration testing |  | 2013-11-20 | 2013-11-24 |  |  | 0% | bar: Semester I 8
8 | D3: Progess Seminar II | All | 2013-11-14 | 2013-11-20 |  |  | 0% | bar: Semester I 8
9 | D4: Project Report | All | 2013-12-01 | 2013-12-12 |  |  | 5% | bar: Semester I 9 to Semester I 11
10 | D5: Final Presentation | All | 2014-01-03 | 2014-01-08 |  |  | 0% | bar: Semester I 10 to Semester I 15
11 | D6: Individual Report | All | 2014-01-08 | 2014-01-16 |  |  | 0% | bar: Semester I 16

## middle gantt chart
# | TASKS | ASSIGNED TO | ESTIMATED START | ESTIMATED END | ACTUAL START | ACTUAL END | TASK COMPLETION % | Semester I
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | D1: Project Brief | All | 2013-10-01 | 2013-10-07 | 2013-10-01 | 2013-10-07 | 100% | bar: Semester I 2
2 | Project Management | All | 2013-10-07 | 2013-12-08 | 2013-10-07 |  | 92% | bar: Semester I 2 to Semester I 10
2.1 | Documentation Management | All |  | 2013-10-13 |  | 2013-10-13 | 100%
2.2 | Source Code Repository | SA |  |  |  |  | 100% | bar: Semester I 2
2.3 | Risk Analysis | CJ |  |  |  |  | 100% | bar: Semester I 2
2.4 | Skills Analysis | SA |  |  |  |  | 60% | bar: Semester I 2; Semester I 6; Semester I 10
2.5 | Gantt Chart | All |  | 2013-12-08 |  | 2013-10-13 | 100% | bar: Semester I 2
3 | Background Research | All | 2013-10-13 | 2013-10-27 | 2013-10-13 |  | 65% | bar: Semester I 2 to Semester I 4
3.1 | Accessibility + Usability | CF |  |  |  |  | 90% | bar: Semester I 2 to Semester I 3
3.2 | Raspberry Pi + Educational value | KN |  |  |  |  | 70% | bar: Semester I 2 to Semester I 3
3.3 | CECIL | SA |  |  |  |  | 30% | bar: Semester I 2 to Semester I 3
3.4 | Existing Systems | CJ |  |  |  |  | 70% | bar: Semester I 2 to Semester I 3
4 | Designing User Interface | All | 2013-10-14 | 2013-10-20 |  |  | 57.5% | bar: Semester I 3 to Semester I 4
4.1 | Wireframes | All |  |  |  |  | 90% | bar: Semester I 3
4.2 | UML diagrams | All |  |  |  |  | 25% | bar: Semester I 3 to Semester I 4
4.2.1 | Use Case | CF |  |  | 2013-10-19 | 2013-10-20 | 100% | bar: Semester I 3
4.2.2 | Activity | KN |  |  |  |  | 0% | bar: Semester I 4
4.2.3 | Class | CJ |  |  |  |  | 0% | bar: Semester I 3
4.2.4 | Sequence | SA |  |  |  |  | 0% | bar: Semester I 4; Semester I 13
4 | D2: Progess Seminar I | KN+SA+CJ | 2013-10-17 | 2013-10-23 | 2013-10-17 | 2013-10-23 | 100% | bar: Semester I 3 to Semester I 4; Semester I 13
5 | Implementation | All | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 18.13% | bar: Semester I 3 to Semester I 8; Semester I 13
6.1 | Model | SA+CF | 2013-10-14 | 2013-11-03 | 2013-10-14 |  | 42.5% | bar: Semester I 3 to Semester I 5; Semester I 13
6.1.1 | Lexer & Parser | SA |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5; Semester I 13
6.1.2 | Compiler | SA+CF |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5
6.1.3 | Simulator | SA+CF |  |  |  |  | 10% | bar: Semester I 4 to Semester I 5
6.2 | View | KN | 2013-10-20 | 2013-11-17 |  |  | 0% | bar: Semester I 4 to Semester I 7
6.2.1 | Input Editor | KN |  |  |  |  | 0% | bar: Semester I 4 to Semester I 7; Semester I 13
6.3 | Controller | CJ | 2013-10-20 |  | 2013-10-20 |  | 30% | bar: Semester I 4 to Semester I 7
6.4 | I/O port stubs | SA | 2013-11-17 | 2013-11-24 |  |  | 0% | bar: Semester I 8; Semester I 13
7 | Testing | All | 2013-10-14 | 2013-12-01 | 2013-10-14 |  | 3.333% | bar: Semester I 3 to Semester I 8; Semester I 13
7.1 | User Evaluation |  | 2013-11-25 | 2013-12-01 |  |  | 10% | bar: Semester I 9
7.2 | Unit Testing |  | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 0% | bar: Semester I 3 to Semester I 7; Semester I 13
7.3 | Integration Testing |  | 2013-11-20 | 2013-11-24 |  |  | 0% | bar: Semester I 8
8 | D3: Progess Seminar II | All | 2013-11-14 | 2013-11-20 |  |  | 0% | bar: Semester I 8
8 | D4: Project Report | All | 2013-12-01 | 2013-12-12 |  |  | 5% | bar: Semester I 9 to Semester I 11
10 | D5: Final Presentation | All | 2014-01-03 | 2014-01-08 |  |  | 0% | bar: Semester I 10 to Semester I 11; Semester I 15
11 | D6: Individual Report | All | 2014-01-08 | 2014-01-16 |  |  | 0% | bar: Semester I 16

## final gantt chart
# | TASKS | ASSIGNED TO | ESTIMATED START | ESTIMATED END | ACTUAL START | ACTUAL END | TASK COMPLETION % | Semester I
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | D1: Project Brief | All | 2013-10-01 | 2013-10-07 | 2013-10-01 | 2013-10-07 | 100% | bar: Semester I 2
2 | Project Management | All | 2013-10-07 | 2013-12-08 | 2013-10-07 |  | 92% | bar: Semester I 2 to Semester I 10
2.1 | Documentation Management | All |  | 2013-10-13 |  | 2013-10-13 | 100%
2.2 | Source Code Repository | SA |  |  |  |  | 100% | bar: Semester I 2
2.3 | Risk Analysis | CJ |  |  |  |  | 100% | bar: Semester I 2
2.4 | Skills Analysis | SA |  |  |  |  | 60% | bar: Semester I 2; Semester I 6; Semester I 10
2.5 | Gantt Chart | All |  | 2013-12-08 |  | 2013-10-13 | 100% | bar: Semester I 2
3 | Background Research | All | 2013-10-13 | 2013-10-27 | 2013-10-13 |  | 65% | bar: Semester I 2 to Semester I 4
3.1 | Accessibility + Usability | CF |  |  |  |  | 90% | bar: Semester I 2 to Semester I 3
3.2 | Raspberry Pi + Educational value | KN |  |  |  |  | 70% | bar: Semester I 2 to Semester I 3
3.3 | CECIL | SA |  |  |  |  | 30% | bar: Semester I 2 to Semester I 3
3.4 | Existing Systems | CJ |  |  |  |  | 70% | bar: Semester I 2 to Semester I 3
4 | Designing User Interface | All | 2013-10-14 | 2013-10-20 |  |  | 57.5% | bar: Semester I 3 to Semester I 4
4.1 | Wireframes | All |  |  |  |  | 90% | bar: Semester I 3
4.2 | UML diagrams | All |  |  |  |  | 25% | bar: Semester I 3 to Semester I 4
4.2.1 | Use Case | CF |  |  | 2013-10-19 | 2013-10-20 | 100% | bar: Semester I 3
4.2.2 | Activity | KN |  |  |  |  | 0% | bar: Semester I 4
4.2.3 | Class | CJ |  |  |  |  | 0% | bar: Semester I 3
4.2.4 | Sequence | SA |  |  |  |  | 0% | bar: Semester I 4; Semester I 13
4 | D2: Progess Seminar I | KN+SA+CJ | 2013-10-17 | 2013-10-23 | 2013-10-17 | 2013-10-23 | 100% | bar: Semester I 3 to Semester I 4; Semester I 13
5 | Implementation | All | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 18.13% | bar: Semester I 3 to Semester I 8; Semester I 13
6.1 | Model | SA+CF | 2013-10-14 | 2013-11-03 | 2013-10-14 |  | 42.5% | bar: Semester I 3 to Semester I 5; Semester I 13
6.1.1 | Lexer & Parser | SA |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5; Semester I 13
6.1.2 | Compiler | SA+CF |  |  |  |  | 80% | bar: Semester I 3 to Semester I 5
6.1.3 | Simulator | SA+CF |  |  |  |  | 10% | bar: Semester I 4 to Semester I 5
6.2 | View | KN | 2013-10-20 | 2013-11-17 |  |  | 0% | bar: Semester I 4 to Semester I 7
6.2.1 | Input Editor | KN |  |  |  |  | 0% | bar: Semester I 4 to Semester I 7; Semester I 13
6.3 | Controller | CJ | 2013-10-20 |  | 2013-10-20 |  | 30% | bar: Semester I 4 to Semester I 7
6.4 | I/O port stubs | SA | 2013-11-17 | 2013-11-24 |  |  | 0% | bar: Semester I 8; Semester I 13
7 | Testing | All | 2013-10-14 | 2013-12-01 | 2013-10-14 |  | 3.333% | bar: Semester I 3 to Semester I 8; Semester I 13
7.1 | User Evaluation |  | 2013-11-25 | 2013-12-01 |  |  | 10% | bar: Semester I 9
7.2 | Unit Testing |  | 2013-10-14 | 2013-11-24 | 2013-10-14 |  | 0% | bar: Semester I 3 to Semester I 7; Semester I 13
7.3 | Integration Testing |  | 2013-11-20 | 2013-11-24 |  |  | 0% | bar: Semester I 8
8 | D3: Progess Seminar II | All | 2013-11-14 | 2013-11-20 |  |  | 0% | bar: Semester I 8
8 | D4: Project Report | All | 2013-12-01 | 2013-12-12 |  |  | 5% | bar: Semester I 9 to Semester I 11
10 | D5: Final Presentation | All | 2014-01-03 | 2014-01-08 |  |  | 0% | bar: Semester I 10 to Semester I 11; Semester I 15
11 | D6: Individual Report | All | 2014-01-08 | 2014-01-16 |  |  | 0% | bar: Semester I 16